## Sheet1
Task | Description | Depends on | Task | Days
A | Clear site |  |  | 3
B | Order materials |  |  | 2
C | Put up formwork for slab | Site cleared |  | 1
D | Lay pipes | Site cleared |  | 1
E | Pour concrete | Formwork, Pipes |  | 1
F | Let concrete set | Concrete poured |  | 3
G | Landscaping | Concrete poured |  | 5
H | Put up walls | Concrete set |  | 3
I | Put on roof | Walls are up |  | 2
J | Install wiring | Walls are up |  | 3
K | Put in plumbing | Walls are up |  | 4
L | Clad internal walls | Roof, Wiring, plumbing |  | 2
M | Paint internal walls | Cladding has begun |  | 2
N | Lay carpet | Painting finished |  | 1
O | Open building | Carpet laid |  | 0