## Sheet1
February
|  |  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
TASK | DURATION | RESOURCES | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Find tree | 1 day | Cayla & Jacinta | bar: 9
Build floor | 1 day | Cayla & Jacinta | bar: 10
Build walls | 2 days | Cayla & Jacinta | bar: 11 to 12
Paint walls | 1 day | Cayla | bar: 13
Build roof | 1 day | Jacinta | bar: 13
Plan party | 1 day | Cayla & Jacinta | bar: 14
Party | 2 days | Cayla & Jacinta | bar: 16 to 17
Project Management Plan