# A Building Project

A new factory is being planned.  The project manager draws up a list of tasks, what each task is dependent on finishing first, and the expected duration of each task.

| Task | Depends on | Days |
| --- | --- | --- |
| Clear site |  | 3 |
| Order materials |  | 2 |
| Put up formwork for slab | Site cleared | 1 |
| Lay pipes | Site cleared | 1 |
| Pour concrete | Formwork, Pipes | 1 |
| Let concrete set | Concrete poured | 3 |
| Landscaping | Concrete poured | 5 |
| Put up walls | Concrete set | 3 |
| Put on roof | Walls are up | 2 |
| Install wiring | Walls are up | 3 |
| Put in plumbing | Walls are up | 4 |
| Clad internal walls | Roof, Wiring, plumbing | 2 |
| Paint internal walls | Cladding has begun | 2 |
| Lay carpet | Painting finished | 1 |
| Open building | Carpet laid | 0 |

Using MS Project, Excel or any tool, create a Gantt chart to represent the project.

Questions…

1.	What is the minimum time required to finish every task?

2.	What tasks are on the critical path?

3.	If the concrete took an extra day to set because of rain, what effect would it have on the building's opening date?

4.	If ordering the materials took an extra day, what effect would it have on the building's opening date?

5.	If the roofing took 3 extra days, what effect would it have on the critical path?

6.	How much slack time is there for the wiring task?

7.	Identify a place where lag time could be identified.

8.	Identify a place where lead time could be identified.

9.	What milestone is in the project?

10.	Why does the carpeting have painting as a predecessor?

11.	Why are roofing, wiring and plumbing all dependent on the walls?

12.	If the walls took a day longer than planned, which tasks' durations could be shortened to ensure the project still finished on time?

13.	If the whole project had to be finished early, how could the project manager save time on tasks?