Forest Hill College - SAC42

Organizational  profile

Harry Highpants runs A1 Fitness - a successful personal trainer business for high income professionals. He employs a number of fitness consultants who visit high powered executives to evaluate their fitness and health status, risk factors, and to recommend a program for them to either stay fit, get fit or both. A number of stages of portable device or web based software development has taken place with working software modules written and tested ready for implementation in the field.

The next step is to implement the web solution and host it live on a web site to enable the software to function under the anytime anywhere motto of A1 Fitness.

### Time for the next step

The options for hosting the web site are twofold:

- Host with a commercial organization  or

- Host on A1 Fitness’s premises (a gym with an office and a canteen in the same area that has gas fired cooking facilities) with a new server at the gym with an ADSL account with a well known ISP. A1 are responsible for everything here from Domain Name registration to purchase of hardware, sourcing of an ISP service and securing the network from any risks.

After some deliberation Harry decides he wants to proceed with option 2.

You have been hired to manage the development, implementation and evaluation of this new system.  The proposed installation would take place approximately over the next 4 weeks only working business hours, during which time, a number of tasks would need to be carried out:

| ## TASK | DEPENDENCIES | TIME (days) |
| --- | --- | --- |
| Register Domain name A1fitness.com.au |  | 1 day |
| Delegate the Domain Name |  | 3 days |
| Install Open Source Operating System and custom built PHP and other necessary software on server |  | 1 day |
| Configure service for live operation |  | 1 day |
| Test service with simulated test data |  | 1 day |
| Order new server |  | 5 days |
| Purchase ADSL router |  | 1 day |
| Search and choose appropriate ISP (Internet Service Provider) |  | 1 day |
| Order digital phone line at premises hosting web server |  | 10 days |
| Write user and technical documentation including Disaster Recovery Plan |  | 5 days |
| Train staff |  | 1 day |
| Launch website at a company meeting for fitness consultants |  | 1 day |

The Task    -  100 marks

- Complete the  project management table above by :

  - Reordering the tasks from beginning to end of project and ( 5 marks )

  - Completing the dependencies column  (5 mark)

- Draw a Pert chart showing each task  ( 5 marks )

- List the tasks on the critical path (5 marks).

- List the milestones in the project and describe a potential problem that could occur for each (8 marks).

- In relation to the purchase of the open source operating system and custom built software as well as hardware, describe each of the following factors and how they impact on the project both at the time of implementing the system and maintaining it into the future (20 marks)

|  | Factor | Description | How factor impacts on initial purchase and future maintenance |
| --- | --- | --- | --- |
| 1 | Technical |  |  |
| 2 | Economic – initial and ongoing |  |  |
| 3 | Scheduling |  |  |
| 4 | Reputation of supplier |  |  |
| 5 | Geographic location of supplier |  |  |
| 6 | Compatibility of components |  |  |
| 7 | Ergonomic requirements |  |  |
| 8 | Reliability and robustness of components |  |  |
| 9 | Training requirements to use the hardware and software |  |  |
| 10 | Maintenance options for hardware and sofware |  |  |

- Propose three types of tests that could be carried out on the system to ensure that it is operating correctly? (6 marks)

| Test Name | Description | How test contributes to ensuring system operates correctly |
| --- | --- | --- |

- Complete the following changeover method table. Which method would you recommend for this implementation?  Give two reasons for your choice (10 marks)

| Changeover Method | Description | Advantage | Disadvantage |
| --- | --- | --- | --- |

    - Which changeover method do you recommend for the system ?

    - Give two reasons for your choice

- Describe and contrast user and technical documentation as required for this system. Who will each of documentation be for ? (5 marks)

- List and describe three appropriate training methods that could be used to make it easier for users of the system to operate the new system. (5 marks)

- Outline a backup and recovery system suitable for the new information system (4 marks)

- Outline a satisfactory disaster recovery plan. Are there any risk factors at the current location of the information system?  (5 marks)

- Propose five criteria that could be used to evaluate the success of the new system. (5 marks)

- Describe effects that the implementation could possibly have on each of the following groups: (12 marks)

- Clients

- Personal Trainers

- Harry Highpants