# PERT / GANTT Exercise – Setting up a new school network

# 1 computer lab and 1 class trolley of laptops for the new school buildings

Assume that the personal computers have VISTA or MAC OS and OFFICE  already, and that the sever has SEVER 2008.

There are 2 IT staff  – Jill and Dave.

# Tasks

- Complete the table on the next page

- Create a PERT chart

- Create a GANTT chart

- Research and list what desktops, servers and laptops you will install using the table below. Justify your selections in the Comment colum. (suggested sites – Apple, Dell)

| Type | Cost | Specs | Comment |
| --- | --- | --- | --- |

- Research and list what software needs to be purchased for the workstations/laptops. Include prices, details and a comment about why the software is required.  (Min 5 software items. Suggested site - Edsoft)

| Name | Cost | Details | Comment |
| --- | --- | --- | --- |

| ID Number | Task | Duration (days) | Successor | Predecessor | Person |
| --- | --- | --- | --- | --- | --- |
| 1 | Development Phase | 0 | 2, 4 |  |  |
| 2 | Research and purchase Server | 1 | 2 | 1 |  |
| 3 | Set up server | 1 | 6 | 2 |  |
| 4 | Research and purchase Workstations/Laptops | 2 | 5, 11 | 1 |  |
| 5 | Set up model network and test | 1 | 10, 11 | 2,4 |  |
| 6 | Research and purchase Software |  |  |  |  |
| 7 | Install Software |  |  |  |  |
| 8 | Research and purchase printers, wireless network points, chairs, desks and cabling |  |  |  |  |
| 9 | Implementation Phase | 0 |  |  |  |
| 10 | Transfer old data to new server |  |  |  |  |
| 12 | Set up rooms with printers, desks, etc |  |  |  |  |
| 13 | Set up workstations, laptop trolleys |  |  |  |  |
| 14 | Install cables, wireless network points |  |  |  |  |
| 15 | Prepare user documentation |  |  |  |  |
| 16 | Train staff and students |  |  |  |  |
| 17 | Open network for use (“Commission Project”) | 0 |  |  |  |