## Sheet1
Task Number | Task | Duration (mins) | Dependencies | Start | End
1 | Wake Up | 0 |  | 0 | 0
2 | Get Up | 1 | 1 | 0 | 1
3 | Get Dressed | 5 | 2 | 1 | 6
4 | Make Breakfast | 5 | 2 | 1 | 6
5 | Eat Breakfast | 10 | 4 | 6 | 16
6 | Brush Teeth | 2 | 5 | 16 | 18
7 | Pack Bag | 5 | 2 | 1 | 6
8 | Get in Car | 1 | 3,6,7 | 18 | 19
9 | Drive to School | 60 | 8 | 19 | 79
10 | Arrive at School | 0 | 9 | 79 | 79
Insert Chart
| Select Data | Start Time
Duration
Task List
| Format Axis | Reverse Order
| Format Data Series | No Fill