##### PROJECT MANAGEMENT EXERCISE

You have decided to landscape your garden and think that it would be a good idea to develop a project plan to work out the total cost and how long it will take. You decide to use MS Project project management software to make the job easier.

The tasks to be performed are as follows:

| ##### TASK No. | ##### TASK | WHO BY | DURATION (days) |
| --- | --- | --- | --- |
| 1 | Draw up plans | Landscape Architect | 2 |
| 2 | Engage contractors | You the Owner | 1 |
| 3 | Clear Land | Labourer(2) | 3 |
| 4 | Deliver soil | Garden Supplies | 3 |
| 5 | Deliver plants | Garden Supplies | 4 |
| 6 | Deliver grass | Garden Supplies | 1 |
| 7 | Lay new soil | Gardener(2) | 2 |
| 8 | Lay grass | Gardener(2) | 1 |
| 9 | Plant plants | Gardener | 1 |
| 10 | Build fountain | Carpenter | 0.5 |

##### LABOUR COSTS

| ###### RESOURCE | COST PER HOUR |
| --- | --- |
| Landscape Architect | $90 |
| Labourer | $35 |
| Gardener | $50 |
| Carpenter | $55 |

Note:  Delivery costs are included in the material costs.

##### MATERIAL COSTS

| ###### TASK | ###### MATERIAL | COST |
| --- | --- | --- |
| 4 | Soil | $1000 |
| 5 | Plants (30 @ $25) | $750 |
| 6 | Grass | $1200 |
| 10 | Fountain | $500 |

##### TASK SEQUENCING

- The contractors can be engaged once the plans have been drawn up.

- The soil, plants and grass can be ordered as soon as the contractors are engaged.

- No tasks apart from the delivery of materials can commence until the land has been cleared.

- The plants cannot be planted until the soil has been laid.

- The fountain cannot be built until the grass has been laid.

##### THE CALENDAR

- The project can commence at 8am on 1 August, 2007.

- A normal working week for al resources is Monday to Friday, 8 hours per day.

- Friday 10 August is a holiday.

##### QUESTIONS

- What is the project end date?

- What is the total cost of landscaping the garden?

- Which tasks have some slack time?