Information Processing & Management Project Management Task

This task will be done in a team.

It will contribute 10 marks towards your Unit 4 Outcome 2 SAC.

All tasks must be completed and submitted for correction by Thursday 17th June.

| Team | Task |
| --- | --- |
|  | 1. Report for Equipment Upgrade for school library |
|  | 2. Web–site for IPM Unit 4 |
|  | 3. Creating a network plan and associated user documentation using VISIO |
|  | 4. Electronic Presentation on Careers in IT (providers and support) |
|  | 5. Create a video of the schools network system |

What you need to do.

Follow the SDLC steps and use your Project Management skills and tools.

Analyse and Plan

- Meet and determine what you need to do. Who will be the manager of the project? Give a title to your project. State and write down the goal.

Include the deadline June 17th.

- Record the meeting, take notes.

- Specify the tasks and sub-tasks. Make a list.

- Allocate the tasks.  Each team member to have a copy of allocated tasks and responsibilities.

- Decide what resources you will use. List these resources.

- Prepare an action plan. Estimate times taken to complete each task. Determine dependencies.

- Prepare a Gantt chart, remember to include milestones, consider any lag times, are tasks allocated so that all team members contribute?

Design

- Agree on the design of your output

- Specify the formats and conventions that you will follow

Develop

- Develop your output, carry out the project. Keep each other informed and monitor the progress of each team member. Each team member to keep an on-going record of difficulties experienced, problems, how they were solved, decisions made, things that worked well etc.

- Test it

Implementation

- Prepare user documentation if this is part of your task

Evaluate

- Reflect on your project management skills. Complete a log book to record progress