## Sheet1
Factory Gantt Task Solution
Task | Depends on | Days | D1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Clear site |  | 3 | bar: D1 to 3
Order materials |  | 2 | bar: D1 to 2
Put up formwork | Site cleared | 1 | bar: 4
Lay pipes | Site cleared | 1 | bar: 4
Pour concrete | Formwork, Pipes | 1 | bar: 5
Let concrete set | Concrete poured | 3 | bar: 6 to 8
Landscaping | Concrete poured | 5 | bar: 6 to 10
Put up walls | Concrete set | 3 | bar: 9 to 11
Put on roof | Walls are up | 2 | bar: 12 to 13
Install wiring | Walls are up | 3 | bar: 12 to 14
Put in plumbing | Walls are up | 4 | bar: 12 to 15
Clad internal walls | Roof, Wiring, plumbing | 2 | bar: 16 to 17
Paint internal walls | Cladding has begun | 2 | bar: 17 to 18
Lay carpet | Painting | 1 | bar: 19
Open building | Carpet laid | 0 | bar: 20
Teacher's Notes - Letting concrete set would be better implemented by using lag time.
Starting the painting while cladding is still being finished is a way of exemplifying lead time.
Critical path: clear, formwork, pour, set, walls, plumbing, clad, paint [assuming milestones are events, not tasks]
I realise the critical path gets "iffy" when the lead time starts - not 100% sure if both tasks are critical
Answers
1. 19 days, not including the milestone which is an event after the last task ends.
2. Clear site, formwork, pour, set, walls, plumbing, clad, paint, carpet [don't include the milestone: it's not a task]
3. Since it's on the critical path, it would make the project take a day longer.
4. No effect because it has a day's slack.
5. The critical path would change because the old critical path would no longer be the longest. It would now be
… Clear site, formwork, pour, set, walls, roofing, clad, paint, carpet.
Task | Depends on | Days | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Put on roof | Walls are up | 2 | bar: 12 to 16
Install wiring | Walls are up | 3 | bar: 12 to 14
Put in plumbing | Walls are up | 4 | bar: 12 to 15
Clad internal walls | Roof, Wiring, plumbing | 2 | bar: 17 to 18
Paint internal walls | Cladding has begun | 2 | bar: 18 to 19
Lay carpet | Painting finished | 1 | bar: 20
Open building | Carpet laid | 0 | bar: 21
6. 1 day
7. The time taken for the cement to set - no task is actually being done, but the walls must wait nevertheless.
8. Starting painting after cladding has begun, but cladding has not been finished.
9. Opening the building.
10. So you don't get paint all over the carpet!
11. The walls support the roof, and wiring/plumbing must travel through the walls.
12. Any of the critical tasks after it - plumbing, cladding, painting, carpeting
13. Put more workers on a task, automate the task (e.g. nailgun instead of hammer), work overtime/weekends, pay bonuses for increased performance etc.
Mark Kelly 2006 | Version 1