INFORMATION TECHNOLOGY

Project Management

Poole, Stewart and Miller, a growing engineering company, are looking to substantially upgrade their information system. They employ Glover-Thomas Management Services to oversee the upgrade. The Project Manager, Peter Thomas, uses project management software to schedule and cost the project. Your task is to check his calculations using Minuteman. The tasks to be performed are as follows:

Task						Who by				Duration (days)

1.	Start											0

2.	Engage Project Manager		Company					1

3.	Analyse current system		Systems Analyst				4

4. 	Design new system			Systems Analyst				3

5.	Write/adapt software			Programmers (2)				4

6.	Purchase hardware/furniture		Project Manager				1

7.	Install hardware			Technicians (2)					2

8.	Load software				Programmers (2)				1.5

9.	Convert data				Programmers (2)				2

10.	Test new system			Systems Analyst				2

11.	Evaluate new system			Systems Analyst				2

12.	Commission new system		Company					1

13.	End											0

Labour Costs:

| # Resource | # Cost per hour |
| --- | --- |
| ### Project Manager | $80 |
| ### Systems Analyst | $90 |
| Programmer | $75 |
| Technician | $60 |

## Material Costs:

| # Task | # Materials/Expeditures | # Total Cost |
| --- | --- | --- |
| 6 | ### Hardware | $45000 |
| 6 | Cabling | $1400 |
| 6 | ### Furniture | $3600 |

Task sequencing:

- The Systems Analyst can be employed once the Project Manager has been engaged

- The new system can’t be designed until the current system has been analysed

- The software can’t be written until the new system is designed

- The hardware can be purchased as soon as the new system has been designed

- The hardware can’t be installed until it has been purchased!

- The software can’t be loaded until the hardware has been installed and the software written

- The data can’t be converted until the software has been installed

- The new system can’t be tested until the software has been installed and the data converted

- The new system can’t be evaluated until it has been tested

- The new system won’t be commissioned until it has been evaluated

The Calendar:

- The project will commence at 9am on Monday 3/4/2006. The working day is 9am-12 and 12-5pm

- A normal working week is Monday – Friday 9am-5pm

Questions:

- What is the project end date?

- What is the total cost of the new system?

- Which tasks have some slack time?