INFORMATION TECHNOLOGY

Project Management

Henriksen, Hill and McHutchison, a growing engineering company, are looking to substantially upgrade their information system. They employ Gainger Management Services to oversee the upgrade. The Project Manager, David Davis, uses project management software to schedule and cost the project. Your task is to check his calculations using Minuteman. The tasks to be performed are as follows:

Task						Who by					Duration (days)

1.	Engage Project Manager		Company					0

2.	Analyse current system		Systems Analyst				4

3. 	Design new system			Systems Analyst				3

4.	Write/adapt software			Programmers (2)				4

5.	Purchase hardware			Project Manager				1

6.	Install hardware			Technician					2

7.	Load software				Programmer (2)				1.5

8.	Convert data				Programmer					2

9.	Test new system			Systems analyst				2

10.	Evaluate new system			Systems analyst				2

11.	Commission new system		Company					0

Labour Costs:

| # Resource | # Cost per hour |
| --- | --- |
| ### Project Manager | $80 |
| ### Systems Analyst | $90 |
| Programmer | $75 |
| Technician | $60 |

## Material Costs:

| # Task | # Material | # Total Cost |
| --- | --- | --- |
| 4 | ### Software license | $2000 |
| 5 | ### Hardware | $45000 |
| 5 | Cabling | $1400 |
| 5 | ### Furniture | $3600 |

Task sequencing:

- The Systems Analyst can be employed once the Project Manager has been engaged

- The software can’t be written until the new system is designed

- The hardware can be purchased as soon as the new system has been designed

- The hardware can’t be installed until it has been purchased!

- The software can’t be loaded until the hardware has been installed

- The data can’t be converted until the software has been installed

- The new system can’t be tested until the software has been installed and the data converted

- The new system can’t be evaluated until it has been tested

- The new system won’t be commissioned until it has been evaluated

The Calendar:

- The project will commence at 8am on Monday 3/8/2004

- A normal working week is Monday – Friday 9am-5pm

Questions:

- What is the project end date?

- What is the total cost of the new system?

- Which tasks have some slack time?